## Activity Log
Team Name: |  |  | bkd Games |  |  | Total Work Time: |  |  | 36.05
Member Name: |  |  | Dominik Pajak |  |  | Development Week:
Task | Activity Description (Anticipated Completion Results) | [7 empty] | ESTIMATED Time in Hours
1 | Story behind game, researching game engines, meeting as a group, basic designs and wireframes | [7 empty] | 10 hours
| Sun | Mon | Tue | Wed | Thur | Fri | Sat | Sun | Actual Time in Hours
| 1 | 1.3 | 0.45 | 1 | 1.3 | 1 | 1 | 0.3 | 7.35
Task | Activity Description (Anticipated Completion Results) | [7 empty] | ESTIMATED Time in Hours
2 | Research, Decide on Version Control System, Update team charter, creation of time table, creation of pitch document | [7 empty] | 15
| Sun | Mon | Tue | Wed | Thur | Fri | Sat | Sun | Actual Time in Hours
| 2 | 2 | 2 | 1.3 | 1.3 | 1.3 | 3.3 | 1.3 | 14.5
Task | Activity Description (Anticipated Completion Results) | [7 empty] | ESTIMATED Time in Hours
3 | Update Pitch Document, Internal and External Needs, Timeline Creation, Animation Storyboard Creation (In progress) | [7 empty] | 15
| Sun | Mon | Tue | Wed | Thur | Fri | Sat | Sun | Actual Time in Hours
| 1.3 | 2 | 1.3 | 2 | 2 | 1.3 | 3 | 1.3 | 14.2
Task | Activity Description (Anticipated Completion Results) | [7 empty] | ESTIMATED Time in Hours
4 | Task list assignments (update), Wireframes with labels, tech, evalutaion, game sketch, game flow chart, site flow chart, game animation storyboard | [7 empty] | 15
| Sun | Mon | Tue | Wed | Thur | Fri | Sat | Sun | Actual Time in Hours
| 2 | 2 | 1.3 | 2 | 1.3 | 2 | 2.3 | 2 | 14.9
Task | Activity Description (Anticipated Completion Results) | [7 empty] | ESTIMATED Time in Hours
5 | Completed logo design, Finished storyboard of intro animation, Created game layout, Assisted with UML creation | [7 empty] | 15
| Sun | Mon | Tue | Wed | Thur | Fri | Sat | Sun | Actual Time in Hours
| 2 | 2 | 2 | 1.3 | 1.3 | 1.3 | 2.3 | 2 | 14.2
Task | Activity Description (Anticipated Completion Results) | [7 empty] | ESTIMATED Time in Hours
6 | Completed logo (colored), Assisted with UML creation, Began creating intro animation in Flash - Updated Background (complete), Created Eye (complete) | [7 empty] | 15
| Sun | Mon | Tue | Wed | Thur | Fri | Sat | Sun | Actual Time in Hours
| 2.3 | 2 | 1.3 | 4 | 2 | 2 | 1 | 2 | 16.6
Task | Activity Description (Anticipated Completion Results) | [7 empty] | ESTIMATED Time in Hours
7 | Found and purchased audio files (Purchased by Kyle), Edited audio files for the animation, Imported audio files into animation, Completed intro scene animation | [7 empty] | 15
| Sun | Mon | Tue | Wed | Thur | Fri | Sat | Sun | Actual Time in Hours
| 2 | 4 | 3 | 2 | 2 | 2 | 2 | 3 | 20
Task | Activity Description (Anticipated Completion Results) | [7 empty] | ESTIMATED Time in Hours
8
| Sun | Mon | Tue | Wed | Thur | Fri | Sat | Sun | Actual Time in Hours
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0