## Sheet1
Tasks | Member | Expected Time | Completion
Create Team Charter | Kyle | 1hr | done
Create Pitch | Kyle | on going | done
Find and Set up VCS | Dom | 1d | done | github/dropdox
Create logo | Brandon | 2hr | done
Create task list | Kyle | on going | done
Create Web Design Doc |  | 1d | in progress
Create Game Design Doc |  | 1d | in progress
Create Time Table | Kyle | 1d | done
Create Tech Evluation Doc |  | 1d | in progress
Proof of Concept | Brandon | 2d | in progress
Create Wire Frame (Web) |  | 5hr | in progress
Index Page | Brandon | 1hr | in progress
Game Page |  | 2d | in progress
Leader Board page |  | 3d | in progress
Contact Us Page |  | 2w | in progress
Storyboard |  | 2d | in progress
Wireframe Map |  |  | in progress
Wireframe Game